## Guide
Project Management KPI Tracker – User Guide
Covers all 16 KPIs: target setting → data capture → automatic calculation → RAG monitoring → corrective actions → verified improvement.
HOW IT WORKS – MONTHLY CYCLE
1. Set targets | KPI_Targets: set Target, Amber limit, Direction and Owner for each KPI. Any later change → one row in Target_Revisions (date, old/new, reason, approver).
2. Capture data | Fill the green-tab logs during the month (Projects, Cost_Schedule, Change_Log, Risk_Log, Issue_Log, Stakeholder_Survey, Resources, Milestones, Quality_Log, Benefits_Log, CI_Log). Only type in YELLOW cells; grey cells calculate.
3. Review | KPI_Tracking calculates every KPI per month and colours it GREEN / AMBER / RED. Dashboard shows the selected month, trend vs previous month and the portfolio snapshot. Trends shows all 16 charts.
4. Act | For every AMBER/RED KPI open a row in Action_Log: value before, root cause, action, owner, due date. Due status flags OVERDUE automatically.
5. Verify the change | When implemented, enter the date and the KPI value after. 'Result' shows Improved / No change / Worse (direction-aware). Process improvements go to CI_Log with 'Benefit verified'.
6. Close the month | Settings › Current reporting month defaults to today's month. Overwrite it with a fixed date to freeze a reported period.
SHEET MAP
Dashboard | One-page view: RAG tiles, 16 KPI table (target, actual, previous, trend, status, actions), portfolio snapshot, 7 charts.
KPI_Tracking | Engine: monthly actuals (12 months) for all 16 KPIs, latest value, RAG grid, count of GREEN/AMBER/RED per month.
Trends | 16 charts – bars = actual, dashed red line = target.
KPI_Targets | Definitions, calculation method, unit, direction, target, amber limit, owner, watch-outs.
Target_Revisions | Audit trail of target changes.
Action_Log | Corrective actions / implemented changes with before–after effectiveness check.
Projects | Register → On-Time Delivery (#4) and Project Success Rate (#10).
Cost_Schedule | Monthly earned value per project → Schedule Variance (#1), Cost Variance (#2), Budget Utilization (#3).
Change_Log | Change requests → Scope Change Frequency (#5) and CR Approval Time (#13).
Risk_Log | Risk register → Risk Mitigation Effectiveness (#6).
Issue_Log | Issues → Issue Resolution Time (#7).
Stakeholder_Survey | Survey scores → Stakeholder Satisfaction (#8).
Resources | Hours and output per team → Resource Utilization (#9) and Team Productivity Index (#14).
Milestones | Baseline vs actual → Milestone Completion Rate (#11).
Quality_Log | Inspections → Project Quality Index (#12).
Benefits_Log | Planned vs realised benefits → Benefits Realization (#15).
CI_Log | Improvement initiatives → Continuous Improvement (#16).
Settings | Year start, current month, budget tolerance, and all drop-down lists.
COLOUR CODE
Yellow cell / blue text | Input – type here.
Grey cell / black text | Formula – do not overwrite.
Green text | Value pulled from another sheet (e.g. targets in KPI_Tracking).
GREEN / AMBER / RED | Higher-is-better KPI: GREEN ≥ target, AMBER ≥ amber limit, else RED. Lower-is-better KPI: GREEN ≤ target, AMBER ≤ amber limit, else RED.
BEFORE YOU USE IT FOR REAL
Sample data | All logs contain realistic sample data (Jan–Oct 2026) so you can see the dashboard working. Select the yellow cells in each log and press Delete – keep the grey formula columns.
Dates | Months in Cost_Schedule and Resources must be the 1st of the month. All logs accept ~500 rows (Projects 100).
Missing data | If a log has no entry for a month, that KPI shows blank (not zero) and is counted as NO DATA on the Dashboard.
Charts | Blank months show no bar. Add rows inside the existing ranges – formulas already cover them.
KPI DESIGN CHALLENGES – read once
Overlaps | Budget Utilization alone is misleading: 100% of budget spent on 70% of the work looks 'perfect'. Always read it with Cost Variance (#2) – that is why both are calculated from the same EVM data.
Schedule variance | The picture says 'timelines'. Date-only variance hides partial progress; this workbook uses earned value (SV%) and keeps milestone dates in #11 and project finish dates in #4.
Small samples | On-Time Delivery and Success Rate run YTD because only a few projects finish per month. One late project can move the % by 20+ points – look at the count, not only the %.
Utilisation | Higher is not always better. Sustained >95% resource utilisation means no slack for breakdowns or learning; treat it as a warning, not a win.
Productivity | A 'Team Productivity Index' is only meaningful if each team defines one stable output unit (m drilled, t moved, WOs closed). Changing the unit mid-year breaks the trend.
Continuous improvement | Counting initiatives measures activity, not improvement. Use 'Benefit verified' in CI_Log and the before/after values in Action_Log to prove impact.
Targets | Set targets from your own baseline (last 6–12 months) before stretching them, and log every change – moving targets silently destroys trend credibility.

## Dashboard
PROJECT MANAGEMENT KPI DASHBOARD
Mining Services – Project Portfolio
Reporting month ▶ | 2026-10-01 | ← select a month from the drop-down
KPI status this month | GREEN |  | AMBER |  | RED |  | NO DATA
44% of measured KPIs on target | 7 |  | 4 |  | 5 |  | 0
KPI | Target | Actual | Prev. month | Change | Trend | Status | Open actions | Actions done | PORTFOLIO SNAPSHOT (live)
Project Schedule Variance (SV%) | 0% | -6.703% | -3.427% | -3.276% | ▼ Worse | RED | 0 | 1 | Projects registered | 8
Project Cost Variance (CV%) | 0% | -3.737% | -1.669% | -2.068% | ▼ Worse | AMBER | 1 | 1 | Active projects | 3
Budget Utilization | 100% | 95.49% | 94.42% | 1.072% | ▼ Worse | GREEN | 0 | 0 | Completed projects | 5
On-Time Project Delivery | 90% | 60% | 60% | 0% | ► Stable | RED | 0 | 0 | Total budget (BAC) | 13320000
Scope Change Frequency | 0.5 | 0 | 0 | 0 | ► Stable | GREEN | 0 | 1 | Total forecast cost (EAC) | 13795000
Risk Mitigation Effectiveness | 85% | 81.25% | 76.92% | 4.327% | ▲ Better | AMBER | 0 | 0 | Forecast over(−)/under(+) budget | -475000
Issue Resolution Time | 7 | 5 | 13 | -8 | ▲ Better | GREEN | 0 | 1 | Open risks | 12
Stakeholder Satisfaction | 4 | 3.9167 | 4.3333 | -0.41667 | ▼ Worse | AMBER | 0 | 0 | …of which HIGH | 6
Resource Utilization Rate | 85% | 86.13% | 84.55% | 1.579% | ▲ Better | GREEN | 1 | 0 | Open issues | 1
Project Success Rate | 80% | 60% | 60% | 0% | ► Stable | RED | 0 | 0 | Issues open > 14 days | 0
Milestone Completion Rate | 90% | 25% | 100% | -75% | ▼ Worse | RED | 0 | 1 | Change requests pending | 1
Project Quality Index | 95% | 100% | 100% | 0% | ► Stable | GREEN | 0 | 1 | Approved CR cost impact (YTD) | 449000
Change Request Approval Time | 5 | 5 | 6.6667 | -1.6667 | ▲ Better | GREEN | 0 | 1 | Overdue milestones | 3
Team Productivity Index | 100% | 95.55% | 97.32% | -1.774% | ▼ Worse | AMBER | 1 | 0 | Corrective actions open | 3
Benefits Realization | 90% | 92.26% | 86.63% | 5.63% | ▲ Better | GREEN | 0 | 0 | …of which OVERDUE | 2
Continuous Improvement Initiatives | 2 | 0 | 0 | 0 | ► Stable | RED | 0 | 0 | Actions that improved the KPI | 100%
[9 empty] | CI initiatives implemented (YTD) | 11
[9 empty] | …with benefit verified | 10
[9 empty] | Target revisions logged | 2
TRENDS – key KPIs (all 16 charts on the Trends sheet)
Note on C4: Pick any month from the list to review it (defaults to the current reporting month).

## KPI_Tracking
KPI Tracking – Monthly Actual vs Target
Fully automatic: actuals are calculated from the logs. Months after the current reporting month (Settings) stay blank. Targets come from KPI_Targets.
# | KPI | Unit | Direction | Target | Amber limit | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | Latest actual | Latest status | Months GREEN | Months RED
1 | Project Schedule Variance (SV%) | % | Higher | 0% | -5% | -5.361% | -3.219% | -4.694% | -3.16% | -4.072% | -5.674% | -5.317% | -3.898% | -3.427% | -6.703% |  |  | -6.703% | RED | 0 | 4
2 | Project Cost Variance (CV%) | % | Higher | 0% | -5% | -2.429% | -0.886% | -1.796% | -2.667% | -4.07% | -3.48% | -4.443% | -0.6079% | -1.669% | -3.737% |  |  | -3.737% | AMBER | 0 | 0
3 | Budget Utilization | % | Lower | 100% | 105% | 93.18% | 94.39% | 94.45% | 97.72% | 97.41% | 94.66% | 96.01% | 94.26% | 94.42% | 95.49% |  |  | 95.49% | GREEN | 10 | 0
4 | On-Time Project Delivery | % | Higher | 90% | 80% | 2026-04-01: 100%; 2026-05-01: 100%; 2026-06-01: 50%; 2026-07-01: 33.33%; 2026-08-01: 50%; 2026-09-01: 60%; 2026-10-01: 60% | 60% | RED | 2 | 5
5 | Scope Change Frequency | CRs / project | Lower | 0.5 | 1 | 1 | 0.4 | 0 | 0.28571 | 0.42857 | 0.14286 | 0.16667 | 0 | 0 | 0 |  |  | 0 | GREEN | 9 | 0
6 | Risk Mitigation Effectiveness | % | Higher | 85% | 70% |  |  | 100% | 100% | 100% | 77.78% | 80% | 80% | 76.92% | 81.25% |  |  | 81.25% | AMBER | 3 | 0
7 | Issue Resolution Time | days | Lower | 7 | 14 | 9.25 | 15 | 9.5714 | 4.3333 | 8 | 4.4286 | 10.4286 | 7.4 | 13 | 5 |  |  | 5 | GREEN | 3 | 1
8 | Stakeholder Satisfaction | score /5 | Higher | 4 | 3.5 | 3.3125 | 3.3125 | 3.625 | 3.5 | 3.875 | 3.6875 | 3.9167 | 4.1667 | 4.3333 | 3.9167 |  |  | 3.9167 | AMBER | 2 | 2
9 | Resource Utilization Rate | % | Higher | 85% | 75% | 84.76% | 84.24% | 82.74% | 81.76% | 82.18% | 83.49% | 81.87% | 84.08% | 84.55% | 86.13% |  |  | 86.13% | GREEN | 1 | 0
10 | Project Success Rate | % | Higher | 80% | 65% | 2026-04-01: 100%; 2026-05-01: 100%; 2026-06-01: 50%; 2026-07-01: 33.33%; 2026-08-01: 50%; 2026-09-01: 60%; 2026-10-01: 60% | 60% | RED | 2 | 5
11 | Milestone Completion Rate | % | Higher | 90% | 80% | 40% | 60% | 100% | 80% | 40% | 40% | 50% | 50% | 100% | 25% |  |  | 25% | RED | 2 | 7
12 | Project Quality Index | % | Higher | 95% | 85% | 100% | 80% | 100% | 60% | 80% | 100% | 80% | 100% | 100% | 100% |  |  | 100% | GREEN | 6 | 4
13 | Change Request Approval Time | days | Lower | 5 | 10 | 8.6667 | 9 | 7.6 | 7 | 5.3333 | 4 | 5 | 6 | 6.6667 | 5 |  |  | 5 | GREEN | 3 | 0
14 | Team Productivity Index | index | Higher | 100% | 90% | 96.22% | 90.72% | 96.73% | 96.39% | 98.03% | 94.51% | 101.3% | 96.98% | 97.32% | 95.55% |  |  | 95.55% | AMBER | 1 | 0
15 | Benefits Realization | % | Higher | 90% | 75% | 2026-04-01: 91.66%; 2026-05-01: 88.56%; 2026-06-01: 94.74%; 2026-07-01: 89.5%; 2026-08-01: 86.1%; 2026-09-01: 86.63%; 2026-10-01: 92.26% | 92.26% | GREEN | 3 | 0
16 | Continuous Improvement Initiatives | count | Higher | 2 | 1 | 1 | 2 | 0 | 3 | 1 | 1 | 2 | 1 | 0 | 0 |  |  | 0 | RED | 3 | 3
Monthly RAG status (automatic)
# | KPI |  |  |  |  | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
1 | Project Schedule Variance (SV%) |  |  |  |  | RED | AMBER | AMBER | AMBER | AMBER | RED | RED | AMBER | AMBER | RED
2 | Project Cost Variance (CV%) |  |  |  |  | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER
3 | Budget Utilization |  |  |  |  | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
4 | On-Time Project Delivery |  |  |  |  | 2026-04-01: GREEN; 2026-05-01: GREEN; 2026-06-01: RED; 2026-07-01: RED; 2026-08-01: RED; 2026-09-01: RED; 2026-10-01: RED
5 | Scope Change Frequency |  |  |  |  | AMBER | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
6 | Risk Mitigation Effectiveness | [6 empty] | GREEN | GREEN | GREEN | AMBER | AMBER | AMBER | AMBER | AMBER
7 | Issue Resolution Time |  |  |  |  | AMBER | RED | AMBER | GREEN | AMBER | GREEN | AMBER | AMBER | AMBER | GREEN
8 | Stakeholder Satisfaction |  |  |  |  | RED | RED | AMBER | AMBER | AMBER | AMBER | AMBER | GREEN | GREEN | AMBER
9 | Resource Utilization Rate |  |  |  |  | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | GREEN
10 | Project Success Rate |  |  |  |  | 2026-04-01: GREEN; 2026-05-01: GREEN; 2026-06-01: RED; 2026-07-01: RED; 2026-08-01: RED; 2026-09-01: RED; 2026-10-01: RED
11 | Milestone Completion Rate |  |  |  |  | RED | RED | GREEN | AMBER | RED | RED | RED | RED | GREEN | RED
12 | Project Quality Index |  |  |  |  | GREEN | RED | GREEN | RED | RED | GREEN | RED | GREEN | GREEN | GREEN
13 | Change Request Approval Time |  |  |  |  | AMBER | AMBER | AMBER | AMBER | AMBER | GREEN | GREEN | AMBER | AMBER | GREEN
14 | Team Productivity Index |  |  |  |  | AMBER | AMBER | AMBER | AMBER | AMBER | AMBER | GREEN | AMBER | AMBER | AMBER
15 | Benefits Realization |  |  |  |  | 2026-04-01: GREEN; 2026-05-01: AMBER; 2026-06-01: GREEN; 2026-07-01: AMBER; 2026-08-01: AMBER; 2026-09-01: AMBER; 2026-10-01: GREEN
16 | Continuous Improvement Initiatives |  |  |  |  | AMBER | GREEN | RED | GREEN | AMBER | AMBER | GREEN | AMBER | RED | RED
| KPIs GREEN |  |  |  |  | 2 | 3 | 5 | 8 | 5 | 6 | 5 | 4 | 5 | 7 | 0 | 0
| KPIs AMBER |  |  |  |  | 7 | 5 | 7 | 7 | 9 | 6 | 6 | 9 | 8 | 4 | 0 | 0
| KPIs RED |  |  |  |  | 3 | 4 | 1 | 1 | 2 | 4 | 5 | 3 | 3 | 5 | 0 | 0
| % KPIs on target |  |  |  |  | 16.67% | 25% | 38.46% | 50% | 31.25% | 37.5% | 31.25% | 25% | 31.25% | 43.75%

## Trends
KPI Trend Charts
Bars = monthly actual · Line = target. Charts update automatically from KPI_Tracking.
Rows below hold the target line series used by the charts – do not delete.
Target series (chart helper – do not delete)
Project Schedule Variance (SV%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Project Cost Variance (CV%) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Budget Utilization | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
On-Time Project Delivery | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Scope Change Frequency | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Risk Mitigation Effectiveness | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
Issue Resolution Time | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Stakeholder Satisfaction | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Resource Utilization Rate | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
Project Success Rate | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
Milestone Completion Rate | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Project Quality Index | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
Change Request Approval Time | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Team Productivity Index | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Benefits Realization | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Continuous Improvement Initiatives | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2

## KPI_Targets
KPI Targets & Definitions
Set the TARGET and AMBER LIMIT per KPI (yellow). Direction: Higher = bigger is better, Lower = smaller is better. Any change → log it in Target_Revisions.
# | KPI | What it measures | Calculation used in this workbook | Unit | Direction | Target (Green) | Amber limit | Frequency | Data source sheet | Basis | Owner | Notes / watch-outs
1 | Project Schedule Variance (SV%) | Deviation between planned and actual project progress/timeline. | (EV − PV) ÷ PV for the month, all projects. Negative = behind schedule. SPI = EV ÷ PV shown in Cost_Schedule. | % | Higher | 0% | -5% | Monthly | Cost_Schedule | Month | A. Camara | Earned-value based – measures work done vs plan, not just dates.
2 | Project Cost Variance (CV%) | Difference between planned (earned) and actual project costs. | (EV − AC) ÷ EV for the month. Negative = over cost. CPI = EV ÷ AC shown in Cost_Schedule. | % | Higher | 0% | -5% | Monthly | Cost_Schedule | Month | M. Diallo | Compares cost against value earned – the honest cost KPI.
3 | Budget Utilization | How efficiently approved budgets are being consumed. | Actual spend (AC) ÷ approved period budget. | % | Lower | 100% | 105% | Monthly | Cost_Schedule | Month | S. Keita | Read with CV%: 100% spend on 70% of work is NOT good. Big under-spend usually means slippage.
4 | On-Time Project Delivery | % of projects delivered within schedule. | Completed projects with Actual finish ≤ Baseline finish ÷ Completed projects (YTD). | % | Higher | 90% | 80% | Monthly | Projects | YTD | F. Bah | Small sample sizes swing this – check the count of completed projects.
5 | Scope Change Frequency | How often project scope changes occur. | Scope change requests submitted in month ÷ active projects in month. | CRs / project | Lower | 0.5 | 1 | Monthly | Change_Log + Projects | Month | I. Sylla | Normalised per active project so a bigger portfolio isn't penalised.
6 | Risk Mitigation Effectiveness | How well project risks are managed and reduced. | Risks closed YTD that did NOT materialise ÷ all risks closed YTD. | % | Higher | 85% | 70% | Monthly | Risk_Log | YTD | K. Conde | Residual score columns in Risk_Log show the reduction achieved per risk.
7 | Issue Resolution Time | How quickly project issues are resolved. | Average days from Date raised to Date resolved, issues resolved in month. | days | Lower | 7 | 14 | Monthly | Issue_Log | Month | O. Traore | Ageing of still-open issues is visible in Issue_Log (days open).
8 | Stakeholder Satisfaction | Stakeholder perception of project outcomes. | Average overall survey score (1–5) of surveys dated in month. | score /5 | Higher | 4 | 3.5 | Monthly / per survey | Stakeholder_Survey | Month | B. Toure | Overall = average of 4 criteria. Track response count too – 2 surveys is not a trend.
9 | Resource Utilization Rate | Efficiency of project resource allocation. | Hours allocated to project work ÷ hours available, all teams. | % | Higher | 85% | 75% | Monthly | Resources | Month | A. Camara | Above ~95% for long periods = burnout/no slack. Watch it, don't just maximise it.
10 | Project Success Rate | % of projects meeting scope, cost and schedule goals. | Completed projects that are On time AND Within budget AND Scope delivered ÷ completed projects (YTD). | % | Higher | 80% | 65% | Monthly | Projects | YTD | M. Diallo | All three criteria must be met – stricter than On-Time Delivery.
11 | Milestone Completion Rate | Timely completion of key project milestones. | Milestones due in month completed on/before baseline date ÷ milestones due in month. | % | Higher | 90% | 80% | Monthly | Milestones | Month | S. Keita | Use baseline dates – re-baselining hides slippage.
12 | Project Quality Index | Quality of project deliverables. | Deliverables accepted first time (no rework) ÷ deliverables inspected in month. | % | Higher | 95% | 85% | Monthly | Quality_Log | Month | F. Bah | First-pass yield. Defects & rework hours are logged for root-cause analysis.
13 | Change Request Approval Time | How quickly change requests are reviewed and decided. | Average days from Date submitted to Decision date, CRs decided in month. | days | Lower | 5 | 10 | Monthly | Change_Log | Month | I. Sylla | Pending CRs are counted on the Dashboard – a fast average can hide a stuck backlog.
14 | Team Productivity Index | Efficiency and output of project teams. | Average of (actual output ÷ planned output) across teams in month. | index | Higher | 100% | 90% | Monthly | Resources | Month | K. Conde | Each team defines its own output unit (m drilled, t moved, drawings…). 100% = plan achieved.
15 | Benefits Realization | Whether project objectives and expected benefits are achieved. | Cumulative realised benefit value ÷ cumulative planned benefit value, benefits measured in month. | % | Higher | 90% | 75% | Monthly / quarterly | Benefits_Log | Month | O. Traore | Benefits often land after handover – keep measuring after project closure.
16 | Continuous Improvement Initiatives | Ongoing improvements in project delivery processes. | Number of improvement initiatives implemented in month. | count | Higher | 2 | 1 | Monthly | CI_Log | Month | B. Toure | Count is the activity; 'Benefit verified' in CI_Log shows whether it actually worked.
RAG rule – Direction = Higher: GREEN if Actual ≥ Target · AMBER if Actual ≥ Amber limit · else RED.
RAG rule – Direction = Lower: GREEN if Actual ≤ Target · AMBER if Actual ≤ Amber limit · else RED.
So for 'Higher' KPIs the amber limit sits BELOW the target; for 'Lower' KPIs it sits ABOVE the target.

## Target_Revisions
Target Revision Log
Every change to a target or amber limit, with the reason and approver – the audit trail for target setting.
Rev # | Date | KPI | Old target | New target | Old amber | New amber | Reason for change | Proposed by | Approved by
1 | 2026-01-05 | On-Time Project Delivery | 85% | 90% | 75% | 80% | Annual target setting – raised after 2025 actual of 88%. | A. Camara | B. Toure
2 | 2026-04-02 | Issue Resolution Time | 10 | 7 | 20 | 14 | Issue triage process introduced (CI-003); faster target now achievable. | M. Diallo | B. Toure

## Action_Log
Corrective Action & Change Implementation Log
When a KPI goes AMBER/RED: record the root cause, the action, who/when, and the KPI value before and after. Result is calculated automatically.
Enter KPI values as decimals for % KPIs (e.g. 0.82 = 82%).
Action ID | Date raised | KPI concerned | Project ID (optional) | KPI value before | Problem / root cause | Corrective action / change | Owner | Due date | Status | Date implemented | KPI value after | Result | Due status | Remarks
A-001 | 2026-02-03 | Project Schedule Variance (SV%) | P01 | -0.08 | Pushback behind plan – one excavator down 3 weeks | Hire-in excavator + double-shift loading | A. Camara | 2026-02-28 | Implemented | 2026-02-20 | -0.03 | Improved | Closed
A-002 | 2026-02-10 | Issue Resolution Time |  | 15.5 | Issues waiting for weekly meeting to be actioned | Daily issue triage at pre-start (CI-003) | M. Diallo | 2026-03-15 | Implemented | 2026-03-10 | 8.2 | Improved | Closed
A-003 | 2026-03-05 | Change Request Approval Time |  | 9.5 | CRs sit with sponsor without deadline | 48h review SLA + standard CR form (CI-002) | B. Toure | 2026-03-31 | Implemented | 2026-03-25 | 6 | Improved | Closed
A-004 | 2026-04-08 | Project Cost Variance (CV%) | P05 | -0.07 | Steel price escalation not in budget | Re-tender steel package; apply rise-and-fall | I. Sylla | 2026-05-15 | Implemented | 2026-05-12 | -0.05 | Improved | Closed
A-005 | 2026-05-06 | Project Quality Index |  | 0.8 | Concrete pours rejected – slump & cover | Pre-pour QA checklist and supplier briefing | S. Keita | 2026-05-30 | Implemented | 2026-06-02 | 0.9 | Improved | Closed
A-006 | 2026-06-04 | Scope Change Frequency |  | 1.1 | Client adding scope informally on site | Scope freeze gate + all requests via CR form | K. Conde | 2026-07-15 | Implemented | 2026-07-10 | 0.6 | Improved | Closed
A-007 | 2026-08-05 | Milestone Completion Rate | P07 | 0.75 | Pump delivery late – milestones slipping | Expedite with supplier, re-sequence install | A. Camara | 2026-09-15 | Implemented | 2026-09-20 | 0.83 | Improved | Closed
A-008 | 2026-09-07 | Team Productivity Index |  | 0.91 | Drill rig waiting on survey pickups | Dedicated surveyor for D&B on day shift | F. Bah | 2026-10-15 | In progress |  |  |  | OVERDUE
A-009 | 2026-10-06 | Project Cost Variance (CV%) | P07 | -0.06 | Overtime on dewatering install | Review crew size and roster | A. Camara | 2026-10-20 | Open |  |  |  | OVERDUE
A-010 | 2026-10-08 | Resource Utilization Rate |  | 0.78 | Maintenance team low booked hours | Assign planned work orders to idle hours | S. Keita | 2026-11-15 | Open |  |  |  | On track
Formulas:
Due status = IF([Date raised]="","",IF(OR([Status]="Implemented",[Status]="Cancelled"),"Closed",IF(AND([Due date]<>"",[Due date]<TODAY()),"OVERDUE","On track")))

## Projects
Project Register
One row per project. Status, baseline vs actual finish and final cost drive On-Time Delivery and Project Success Rate.
Project ID | Project name | Area / client | Project manager | Sponsor | Start date | Baseline finish | Forecast / actual finish | Status | Budget at completion (BAC) | Forecast / final cost (EAC) | Scope fully delivered? | Deliverables accepted? | On time? | Within budget? | Successful? | Days late (+) / early (−) | Cost variance at completion | Remarks
P01 | Pit 2 Stage 3 Pushback | Mining | A. Camara | B. Toure | 2025-11-01 | 2026-06-30 | 2026-07-21 | Completed | 4800000 | 5100000 | Yes | Yes | No | No | No | 21 | -300000
P02 | Main Haul Road Upgrade | Infrastructure | M. Diallo | B. Toure | 2026-01-10 | 2026-04-30 | 2026-04-25 | Completed | 1250000 | 1210000 | Yes | Yes | Yes | Yes | Yes | -5 | 40000
P03 | Haul Truck Mid-life Rebuilds | Maintenance | S. Keita | O. Traore | 2026-02-01 | 2026-08-31 | 2026-08-28 | Completed | 2100000 | 2180000 | Yes | Yes | Yes | Yes | Yes | -3 | -80000
P04 | Blast Fragmentation Optimisation | Drill & Blast | F. Bah | B. Toure | 2026-01-15 | 2026-05-31 | 2026-06-20 | Completed | 350000 | 335000 | No | Yes | No | Yes | No | 20 | 15000
P05 | Workshop Extension | Infrastructure | I. Sylla | O. Traore | 2026-03-01 | 2026-11-30 | 2026-12-20 | Active | 1600000 | 1720000 | [5 empty] | 20 | -120000
P06 | ERP Maintenance Module Roll-out | Systems | K. Conde | O. Traore | 2026-04-01 | 2026-12-15 | 2026-12-15 | Active | 420000 | 410000 | [5 empty] | 0 | 10000
P07 | Pit Dewatering System Upgrade | Mining | A. Camara | B. Toure | 2026-05-01 | 2026-10-31 | 2026-11-14 | Active | 900000 | 960000 | [5 empty] | 14 | -60000
P08 | Camp Accommodation Expansion | Infrastructure | M. Diallo | O. Traore | 2026-02-15 | 2026-09-30 | 2026-09-30 | Completed | 1900000 | 1880000 | Yes | No | Yes | Yes | Yes | 0 | 20000

## Cost_Schedule
Cost & Schedule (Earned Value) – monthly per project
Enter one row per project per month. Month = 1st of the month. Values in your currency. PV = budgeted cost of work planned, EV = budgeted cost of work done, AC = actual cost.
Month | Project ID | Project name | Approved budget (period) | Planned value (PV) | Earned value (EV) | Actual cost (AC) | Schedule var. SV = EV−PV | Cost var. CV = EV−AC | SPI = EV/PV | CPI = EV/AC | Budget used = AC/Budget | Comment
2026-01-01 | P01 | Pit 2 Stage 3 Pushback | 600000 | 579700 | 527800 | 564500 | -51900 | -36700 | 0.91047 | 0.93499 | 94.08%
2026-01-01 | P02 | Main Haul Road Upgrade | 312000 | 297500 | 304100 | 292600 | 6600 | 11500 | 1.0222 | 1.0393 | 93.78%
2026-01-01 | P04 | Blast Fragmentation Optimisation | 70000 | 66700 | 61400 | 57900 | -5300 | 3500 | 0.92054 | 1.0604 | 82.71%
2026-02-01 | P01 | Pit 2 Stage 3 Pushback | 600000 | 583000 | 528200 | 546100 | -54800 | -17900 | 0.906 | 0.96722 | 91.02%
2026-02-01 | P02 | Main Haul Road Upgrade | 312000 | 303000 | 315100 | 298700 | 12100 | 16400 | 1.0399 | 1.0549 | 95.74%
2026-02-01 | P03 | Haul Truck Mid-life Rebuilds | 300000 | 288300 | 284700 | 301100 | -3600 | -16400 | 0.98751 | 0.94553 | 100.4%
2026-02-01 | P04 | Blast Fragmentation Optimisation | 70000 | 68500 | 62600 | 62500 | -5900 | 100 | 0.91387 | 1.0016 | 89.29%
2026-02-01 | P08 | Camp Accommodation Expansion | 238000 | 226700 | 231600 | 226400 | 4900 | 5200 | 1.0216 | 1.023 | 95.13%
2026-03-01 | P01 | Pit 2 Stage 3 Pushback | 600000 | 574300 | 521900 | 546900 | -52400 | -25000 | 0.90876 | 0.95429 | 91.15%
2026-03-01 | P02 | Main Haul Road Upgrade | 312000 | 309100 | 309200 | 301400 | 100 | 7800 | 1.0003 | 1.0259 | 96.6%
2026-03-01 | P03 | Haul Truck Mid-life Rebuilds | 300000 | 294600 | 286500 | 295900 | -8100 | -9400 | 0.97251 | 0.96823 | 98.63%
2026-03-01 | P04 | Blast Fragmentation Optimisation | 70000 | 66700 | 59700 | 56900 | -7000 | 2800 | 0.89505 | 1.0492 | 81.29%
2026-03-01 | P05 | Workshop Extension | 178000 | 175200 | 165700 | 175300 | -9500 | -9600 | 0.94578 | 0.94524 | 98.48%
2026-03-01 | P08 | Camp Accommodation Expansion | 238000 | 233100 | 232400 | 227300 | -700 | 5100 | 0.997 | 1.0224 | 95.5%
2026-04-01 | P01 | Pit 2 Stage 3 Pushback | 600000 | 593800 | 558800 | 583200 | -35000 | -24400 | 0.94106 | 0.95816 | 97.2%
2026-04-01 | P02 | Main Haul Road Upgrade | 312000 | 305400 | 312000 | 309500 | 6600 | 2500 | 1.0216 | 1.0081 | 99.2%
2026-04-01 | P03 | Haul Truck Mid-life Rebuilds | 300000 | 295900 | 286300 | 303400 | -9600 | -17100 | 0.96756 | 0.94364 | 101.1%
2026-04-01 | P04 | Blast Fragmentation Optimisation | 70000 | 66900 | 61200 | 60300 | -5700 | 900 | 0.9148 | 1.0149 | 86.14%
2026-04-01 | P05 | Workshop Extension | 178000 | 170500 | 161900 | 168400 | -8600 | -6500 | 0.94956 | 0.9614 | 94.61%
2026-04-01 | P06 | ERP Maintenance Module Roll-out | 47000 | 46200 | 46900 | 46200 | 700 | 700 | 1.0152 | 1.0152 | 98.3%
2026-04-01 | P08 | Camp Accommodation Expansion | 238000 | 236500 | 233900 | 234300 | -2600 | -400 | 0.98901 | 0.99829 | 98.45%
2026-05-01 | P01 | Pit 2 Stage 3 Pushback | 600000 | 587800 | 549300 | 580700 | -38500 | -31400 | 0.9345 | 0.94593 | 96.78%
2026-05-01 | P03 | Haul Truck Mid-life Rebuilds | 300000 | 297600 | 299400 | 307900 | 1800 | -8500 | 1.006 | 0.97239 | 102.6%
2026-05-01 | P04 | Blast Fragmentation Optimisation | 70000 | 68800 | 61600 | 60500 | -7200 | 1100 | 0.89535 | 1.0182 | 86.43%
2026-05-01 | P05 | Workshop Extension | 178000 | 174900 | 171100 | 186600 | -3800 | -15500 | 0.97827 | 0.91693 | 104.8%
2026-05-01 | P06 | ERP Maintenance Module Roll-out | 47000 | 45300 | 45000 | 44500 | -300 | 500 | 0.99338 | 1.0112 | 94.68%
2026-05-01 | P07 | Pit Dewatering System Upgrade | 150000 | 142700 | 133800 | 139000 | -8900 | -5200 | 0.93763 | 0.96259 | 92.67%
2026-05-01 | P08 | Camp Accommodation Expansion | 238000 | 227500 | 221500 | 222800 | -6000 | -1300 | 0.97363 | 0.99417 | 93.61%
2026-06-01 | P01 | Pit 2 Stage 3 Pushback | 600000 | 573900 | 525600 | 553500 | -48300 | -27900 | 0.91584 | 0.94959 | 92.25%
2026-06-01 | P03 | Haul Truck Mid-life Rebuilds | 300000 | 298100 | 284800 | 292400 | -13300 | -7600 | 0.95538 | 0.97401 | 97.47%
2026-06-01 | P04 | Blast Fragmentation Optimisation | 70000 | 68400 | 64400 | 63700 | -4000 | 700 | 0.94152 | 1.011 | 91%
2026-06-01 | P05 | Workshop Extension | 178000 | 176800 | 165700 | 176400 | -11100 | -10700 | 0.93722 | 0.93934 | 99.1%
2026-06-01 | P06 | ERP Maintenance Module Roll-out | 47000 | 45500 | 46500 | 46800 | 1000 | -300 | 1.022 | 0.99359 | 99.57%
2026-06-01 | P07 | Pit Dewatering System Upgrade | 150000 | 143600 | 132400 | 138100 | -11200 | -5700 | 0.92201 | 0.95873 | 92.07%
2026-06-01 | P08 | Camp Accommodation Expansion | 238000 | 228900 | 228700 | 227600 | -200 | 1100 | 0.99913 | 1.0048 | 95.63%
2026-07-01 | P01 | Pit 2 Stage 3 Pushback | 600000 | 577900 | 521500 | 550100 | -56400 | -28600 | 0.90241 | 0.94801 | 91.68%
2026-07-01 | P03 | Haul Truck Mid-life Rebuilds | 300000 | 290500 | 285800 | 302400 | -4700 | -16600 | 0.98382 | 0.94511 | 100.8%
2026-07-01 | P05 | Workshop Extension | 178000 | 175200 | 166600 | 179500 | -8600 | -12900 | 0.95091 | 0.92813 | 100.8%
2026-07-01 | P06 | ERP Maintenance Module Roll-out | 47000 | 46200 | 45000 | 45200 | -1200 | -200 | 0.97403 | 0.99558 | 96.17%
2026-07-01 | P07 | Pit Dewatering System Upgrade | 150000 | 148300 | 142500 | 153700 | -5800 | -11200 | 0.96089 | 0.92713 | 102.5%
2026-07-01 | P08 | Camp Accommodation Expansion | 238000 | 230800 | 229400 | 221700 | -1400 | 7700 | 0.99393 | 1.0347 | 93.15%
2026-08-01 | P03 | Haul Truck Mid-life Rebuilds | 300000 | 294500 | 281000 | 281900 | -13500 | -900 | 0.95416 | 0.99681 | 93.97%
2026-08-01 | P05 | Workshop Extension | 178000 | 171000 | 159200 | 168700 | -11800 | -9500 | 0.93099 | 0.94369 | 94.78%
2026-08-01 | P06 | ERP Maintenance Module Roll-out | 47000 | 44800 | 43500 | 41700 | -1300 | 1800 | 0.97098 | 1.0432 | 88.72%
2026-08-01 | P07 | Pit Dewatering System Upgrade | 150000 | 143300 | 133600 | 137600 | -9700 | -4000 | 0.93231 | 0.97093 | 91.73%
2026-08-01 | P08 | Camp Accommodation Expansion | 238000 | 236500 | 238100 | 230700 | 1600 | 7400 | 1.0068 | 1.0321 | 96.93%
2026-09-01 | P05 | Workshop Extension | 178000 | 171300 | 161200 | 171100 | -10100 | -9900 | 0.94104 | 0.94214 | 96.12%
2026-09-01 | P06 | ERP Maintenance Module Roll-out | 47000 | 44900 | 45800 | 46200 | 900 | -400 | 1.02 | 0.99134 | 98.3%
2026-09-01 | P07 | Pit Dewatering System Upgrade | 150000 | 146000 | 137100 | 141700 | -8900 | -4600 | 0.93904 | 0.96754 | 94.47%
2026-09-01 | P08 | Camp Accommodation Expansion | 238000 | 227300 | 225200 | 219800 | -2100 | 5400 | 0.99076 | 1.0246 | 92.35%
2026-10-01 | P05 | Workshop Extension | 178000 | 176500 | 164300 | 170800 | -12200 | -6500 | 0.93088 | 0.96194 | 95.96%
2026-10-01 | P06 | ERP Maintenance Module Roll-out | 47000 | 46900 | 47000 | 45100 | 100 | 1900 | 1.0021 | 1.0421 | 95.96%
2026-10-01 | P07 | Pit Dewatering System Upgrade | 150000 | 146600 | 133900 | 142200 | -12700 | -8300 | 0.91337 | 0.94163 | 94.8%

## Change_Log
Change Request Log
Every change request (scope, schedule, cost…). Scope CRs drive Scope Change Frequency; submitted→decision days drive CR Approval Time.
CR ID | Project ID | Date submitted | Description of change | Change type | Requested by | Cost impact | Schedule impact (days) | Decision | Decision date | Approval time (days) | Implemented? | Implementation date | Remarks
CR-001 | P06 | 2026-02-23 | Upgrade concrete spec | Quality | K. Conde | 60000 | 3 | Rejected | 2026-03-02 | 7
CR-002 | P04 | 2026-10-26 | Fuel price escalation | Cost | B. Toure | 40000 | -2 | Rejected | 2026-10-31 | 5
CR-003 | P08 | 2026-01-01 | Additional steel cost | Cost | K. Conde | 40000 | 0 | Approved | 2026-01-14 | 13 | Yes | 2026-01-28
CR-004 | P04 | 2026-04-04 | Add reporting dashboard to ERP | Scope | K. Conde | 60000 | 0 | Approved | 2026-04-13 | 9 | Yes | 2026-04-16
CR-005 | P04 | 2026-02-13 | Fuel price escalation | Cost | O. Traore | -8000 | 10 | Approved | 2026-02-17 | 4 | Yes | 2026-03-02
CR-006 | P03 | 2026-02-24 | Extra drainage culverts | Scope | B. Toure | 60000 | 7 | Approved | 2026-03-07 | 11 | No
CR-007 | P01 | 2026-03-18 | Delay due to rainy season | Schedule | O. Traore | 15000 | 3 | Approved | 2026-03-31 | 13 | Yes | 2026-04-19
CR-008 | P04 | 2026-01-09 | Additional bay in workshop | Scope | O. Traore | 15000 | 0 | Rejected | 2026-01-16 | 7
CR-009 | P07 | 2026-06-15 | Fuel price escalation | Cost | A. Camara | -8000 | 3 | Rejected | 2026-06-19 | 4
CR-010 | P03 | 2026-10-01 | Additional steel cost | Cost | M. Diallo | 25000 | 0 | Pending
CR-011 | P08 | 2026-06-22 | Delay due to rainy season | Schedule | F. Bah | 15000 | 7 | Rejected | 2026-06-25 | 3
CR-012 | P08 | 2026-01-25 | Add ramp widening at bench 4 | Scope | B. Toure | 40000 | 14 | Approved | 2026-02-08 | 14 | No
CR-013 | P05 | 2026-09-20 | Resequence works around blasting | Schedule | F. Bah | -8000 | 3 | Approved | 2026-09-29 | 9 | Yes | 2026-10-09
CR-014 | P06 | 2026-07-04 | Additional bay in workshop | Scope | M. Diallo | 15000 | -2 | Approved | 2026-07-09 | 5 | Yes | 2026-07-18
CR-015 | P03 | 2026-06-05 | Add ramp widening at bench 4 | Scope | O. Traore | -8000 | 3 | Rejected | 2026-06-10 | 5
CR-016 | P07 | 2026-04-06 | Additional steel cost | Cost | A. Camara | 40000 | 14 | Approved | 2026-04-11 | 5 | Yes | 2026-04-16
CR-017 | P07 | 2026-08-15 | Fuel price escalation | Cost | F. Bah | 0 | 0 | Approved | 2026-08-21 | 6 | Yes | 2026-08-26
CR-018 | P03 | 2026-05-09 | Additional bay in workshop | Scope | O. Traore | 15000 | 14 | Approved | 2026-05-13 | 4 | No
CR-019 | P06 | 2026-09-19 | Resequence works around blasting | Schedule | M. Diallo | 40000 | 0 | Approved | 2026-09-21 | 2 | Yes | 2026-09-29
CR-020 | P04 | 2026-02-26 | Extend pushback to east wall | Scope | O. Traore | 40000 | 14 | Approved | 2026-03-01 | 3 | Yes | 2026-03-14
CR-021 | P04 | 2026-03-02 | Resequence works around blasting | Schedule | A. Camara | 15000 | 3 | Rejected | 2026-03-06 | 4
CR-022 | P04 | 2026-05-21 | Additional bay in workshop | Scope | A. Camara | 0 | 0 | Approved | 2026-05-25 | 4 | Yes | 2026-05-28
CR-023 | P08 | 2026-09-18 | Add second excavator crew | Resource | O. Traore | 25000 | 7 | Approved | 2026-09-27 | 9 | Yes | 2026-10-13
CR-024 | P03 | 2026-04-08 | Extra drainage culverts | Scope | A. Camara | 0 | -2 | Approved | 2026-04-15 | 7 | No
CR-025 | P02 | 2026-05-14 | Additional bay in workshop | Scope | F. Bah | 60000 | 7 | Approved | 2026-05-22 | 8 | No
CR-026 | P05 | 2026-01-15 | Extend pushback to east wall | Scope | K. Conde | 15000 | 0 | Approved | 2026-01-21 | 6 | Yes | 2026-02-03

## Risk_Log
Risk Register
Score = Probability × Impact (1–5 each). Closing a risk: enter Closure date and whether it Materialised. Residual score shows the reduction achieved.
Risk ID | Project ID | Date identified | Risk description | Category | Probability (1-5) | Impact (1-5) | Inherent score | Rating | Mitigation action | Owner | Status | Closure date | Materialised? | Residual P (1-5) | Residual I (1-5) | Residual score | Reduction %
R-001 | P01 | 2026-05-07 | Fuel price increase | Commercial | 3 | 2 | 6 | Low | Rise-and-fall clause in contract | M. Diallo | Closed | 2026-05-27 | No | 2 | 1 | 2 | 66.67%
R-002 | P03 | 2026-05-03 | Late delivery of rebuild kits | Supply chain | 5 | 2 | 10 | Medium | Order 8 weeks early, second supplier | O. Traore | Closed | 2026-06-06 | No | 4 | 1 | 4 | 60%
R-003 | P01 | 2026-06-24 | ERP data migration errors | Technical | 3 | 4 | 12 | Medium | Trial migration and reconciliation | O. Traore | Open |  |  | 1 | 4 | 4 | 66.67%
R-004 | P01 | 2026-09-05 | Pit wall instability on east wall | Technical | 3 | 2 | 6 | Low | Geotech monitoring radar + reduced bench height | A. Camara | Closed | 2026-09-28 | No | 1 | 1 | 1 | 83.33%
R-005 | P02 | 2026-09-22 | Flyrock incident near haul road | Safety | 5 | 4 | 20 | High | Blast exclusion zone review, stemming QA | B. Toure | Closed | 2026-10-20 | No | 2 | 2 | 4 | 80%
R-006 | P02 | 2026-05-03 | Community road blockage | Community | 3 | 3 | 9 | Medium | Weekly liaison meetings with village committee | B. Toure | Occurred | 2026-06-28 | Yes | 1 | 2 | 2 | 77.78%
R-007 | P03 | 2026-05-25 | Pit wall instability on east wall | Technical | 3 | 2 | 6 | Low | Geotech monitoring radar + reduced bench height | A. Camara | Mitigated | 2026-06-30 | No | 1 | 1 | 1 | 83.33%
R-008 | P05 | 2026-08-02 | ERP data migration errors | Technical | 4 | 2 | 8 | Medium | Trial migration and reconciliation | I. Sylla | Open |  |  | 1 | 1 | 1 | 87.5%
R-009 | P08 | 2026-08-15 | ERP data migration errors | Technical | 2 | 3 | 6 | Low | Trial migration and reconciliation | M. Diallo | Occurred | 2026-09-04 | Yes | 1 | 2 | 2 | 66.67%
R-010 | P02 | 2026-09-15 | Community road blockage | Community | 5 | 3 | 15 | High | Weekly liaison meetings with village committee | S. Keita | Open |  |  | 4 | 3 | 12 | 20%
R-011 | P04 | 2026-09-09 | Fuel price increase | Commercial | 3 | 4 | 12 | Medium | Rise-and-fall clause in contract | B. Toure | Open |  |  | 1 | 3 | 3 | 75%
R-012 | P07 | 2026-08-13 | Pit wall instability on east wall | Technical | 3 | 2 | 6 | Low | Geotech monitoring radar + reduced bench height | I. Sylla | Open |  |  | 1 | 1 | 1 | 83.33%
R-013 | P04 | 2026-03-14 | Fuel price increase | Commercial | 5 | 4 | 20 | High | Rise-and-fall clause in contract | A. Camara | Mitigated | 2026-04-19 | No | 3 | 4 | 12 | 40%
R-014 | P01 | 2026-05-09 | Fuel price increase | Commercial | 2 | 5 | 10 | Medium | Rise-and-fall clause in contract | I. Sylla | Mitigated | 2026-07-18 | No | 1 | 4 | 4 | 60%
R-015 | P06 | 2026-02-02 | Community road blockage | Community | 3 | 3 | 9 | Medium | Weekly liaison meetings with village committee | F. Bah | Open |  |  | 1 | 1 | 1 | 88.89%
R-016 | P07 | 2026-06-14 | Pit wall instability on east wall | Technical | 5 | 3 | 15 | High | Geotech monitoring radar + reduced bench height | B. Toure | Open |  |  | 4 | 1 | 4 | 73.33%
R-017 | P03 | 2026-10-25 | Late delivery of rebuild kits | Supply chain | 4 | 5 | 20 | High | Order 8 weeks early, second supplier | B. Toure | Open |  |  | 1 | 5 | 5 | 75%
R-018 | P07 | 2026-07-11 | Community road blockage | Community | 4 | 4 | 16 | High | Weekly liaison meetings with village committee | F. Bah | Open |  |  | 1 | 3 | 3 | 81.25%
R-019 | P08 | 2026-05-16 | Key engineer resignation | Schedule | 2 | 3 | 6 | Low | Cross-training and handover notes | K. Conde | Mitigated | 2026-06-04 | No | 1 | 3 | 3 | 50%
R-020 | P05 | 2026-08-14 | Late delivery of rebuild kits | Supply chain | 3 | 3 | 9 | Medium | Order 8 weeks early, second supplier | F. Bah | Mitigated | 2026-09-19 | No | 2 | 2 | 4 | 55.56%
R-021 | P05 | 2026-01-24 | Key engineer resignation | Schedule | 5 | 5 | 25 | High | Cross-training and handover notes | K. Conde | Open |  |  | 4 | 4 | 16 | 36%
R-022 | P04 | 2026-01-16 | Community road blockage | Community | 4 | 3 | 12 | Medium | Weekly liaison meetings with village committee | M. Diallo | Open |  |  | 1 | 1 | 1 | 91.67%
R-023 | P01 | 2026-05-08 | Key engineer resignation | Schedule | 5 | 5 | 25 | High | Cross-training and handover notes | O. Traore | Occurred | 2026-06-11 | Yes | 4 | 5 | 20 | 20%
R-024 | P02 | 2026-08-19 | ERP data migration errors | Technical | 2 | 2 | 4 | Low | Trial migration and reconciliation | F. Bah | Mitigated | 2026-10-25 | No | 1 | 2 | 2 | 50%
R-025 | P01 | 2026-03-05 | Heavy rain flooding pit floor | Environmental | 5 | 2 | 10 | Medium | Upgrade pumps, sump preparation before season | I. Sylla | Closed | 2026-03-22 | No | 4 | 1 | 4 | 60%
R-026 | P04 | 2026-03-21 | Community road blockage | Community | 5 | 2 | 10 | Medium | Weekly liaison meetings with village committee | A. Camara | Closed | 2026-04-24 | No | 3 | 1 | 3 | 70%
R-027 | P08 | 2026-01-18 | Community road blockage | Community | 5 | 4 | 20 | High | Weekly liaison meetings with village committee | F. Bah | Open |  |  | 2 | 4 | 8 | 60%
R-028 | P04 | 2026-09-08 | Pit wall instability on east wall | Technical | 5 | 4 | 20 | High | Geotech monitoring radar + reduced bench height | O. Traore | Mitigated | 2026-10-05 | No | 4 | 3 | 12 | 40%

## Issue_Log
Issue Log
Issues = problems happening now (risks that occurred, defects, blockers). Resolution days feed Issue Resolution Time.
Issue ID | Project ID | Date raised | Issue description | Priority | Owner | Status | Date resolved | Days to resolve | Days open (if open) | Root cause | Remarks
I-001 | P06 | 2026-06-08 | Dust complaint from village | Low | K. Conde | Resolved | 2026-06-09 | 1 |  | Water cart breakdown
I-002 | P05 | 2026-07-07 | Excavator breakdown – no spare boom cylinder | Critical | F. Bah | Resolved | 2026-07-20 | 13 |  | Spares stock-out
I-003 | P04 | 2026-08-07 | ERP user access not granted | High | B. Toure | Resolved | 2026-08-20 | 13 |  | IT approval workflow
I-004 | P08 | 2026-04-09 | ERP user access not granted | High | F. Bah | Resolved | 2026-04-11 | 2 |  | IT approval workflow
I-005 | P03 | 2026-08-14 | Excavator breakdown – no spare boom cylinder | Low | A. Camara | Resolved | 2026-08-24 | 10 |  | Spares stock-out
I-006 | P01 | 2026-04-01 | Concrete batch failed slump test | Critical | S. Keita | Resolved | 2026-04-08 | 7 |  | Supplier QC
I-007 | P02 | 2026-07-15 | Pump discharge line leaking | Critical | S. Keita | Resolved | 2026-07-27 | 12 |  | Poor installation
I-008 | P08 | 2026-06-07 | Concrete batch failed slump test | Critical | I. Sylla | Resolved | 2026-06-18 | 11 |  | Supplier QC
I-009 | P03 | 2026-07-12 | Pump discharge line leaking | Critical | A. Camara | Resolved | 2026-07-20 | 8 |  | Poor installation
I-010 | P07 | 2026-02-09 | Survey pickup missing for bench 3 | Critical | F. Bah | Resolved | 2026-02-21 | 12 |  | Surveyor rostered off
I-011 | P07 | 2026-07-12 | ERP user access not granted | Critical | A. Camara | Resolved | 2026-07-26 | 14 |  | IT approval workflow
I-012 | P08 | 2026-08-07 | Pump discharge line leaking | High | K. Conde | Resolved | 2026-08-16 | 9 |  | Poor installation
I-013 | P07 | 2026-06-24 | Dust complaint from village | High | O. Traore | Resolved | 2026-06-25 | 1 |  | Water cart breakdown
I-014 | P02 | 2026-01-13 | Excavator breakdown – no spare boom cylinder | Critical | I. Sylla | Resolved | 2026-01-28 | 15 |  | Spares stock-out
I-015 | P06 | 2026-04-24 | Survey pickup missing for bench 3 | Medium | I. Sylla | Resolved | 2026-05-04 | 10 |  | Surveyor rostered off
I-016 | P06 | 2026-06-20 | Excavator breakdown – no spare boom cylinder | Medium | I. Sylla | Resolved | 2026-06-25 | 5 |  | Spares stock-out
I-017 | P04 | 2026-01-24 | Survey pickup missing for bench 3 | Critical | B. Toure | Resolved | 2026-01-25 | 1 |  | Surveyor rostered off
I-018 | P05 | 2026-08-25 | Contractor invoice disputed | Low | B. Toure | Resolved | 2026-09-07 | 13 |  | Unclear rates
I-019 | P05 | 2026-03-16 | Concrete batch failed slump test | High | F. Bah | Resolved | 2026-03-17 | 1 |  | Supplier QC
I-020 | P02 | 2026-06-11 | Dust complaint from village | High | O. Traore | Resolved | 2026-06-17 | 6 |  | Water cart breakdown
I-021 | P01 | 2026-03-08 | Contractor invoice disputed | Low | K. Conde | Resolved | 2026-03-11 | 3 |  | Unclear rates
I-022 | P05 | 2026-03-14 | Survey pickup missing for bench 3 | Critical | F. Bah | Resolved | 2026-03-17 | 3 |  | Surveyor rostered off
I-023 | P03 | 2026-02-14 | Dust complaint from village | High | S. Keita | Resolved | 2026-03-01 | 15 |  | Water cart breakdown
I-024 | P02 | 2026-07-15 | Blast delayed – explosives truck late | Medium | I. Sylla | Resolved | 2026-07-27 | 12 |  | Logistics
I-025 | P05 | 2026-05-19 | ERP user access not granted | Medium | F. Bah | Resolved | 2026-05-25 | 6 |  | IT approval workflow
I-026 | P04 | 2026-08-08 | Concrete batch failed slump test | High | I. Sylla | Resolved | 2026-08-12 | 4 |  | Supplier QC
I-027 | P04 | 2026-10-07 | Pump discharge line leaking | High | M. Diallo | Resolved | 2026-10-12 | 5 |  | Poor installation
I-028 | P08 | 2026-08-02 | Survey pickup missing for bench 3 | High | B. Toure | Resolved | 2026-08-03 | 1 |  | Surveyor rostered off
I-029 | P02 | 2026-06-02 | ERP user access not granted | Critical | F. Bah | Resolved | 2026-06-06 | 4 |  | IT approval workflow
I-030 | P03 | 2026-10-19 | Blast delayed – explosives truck late | Low | I. Sylla | In progress |  |  | 10 | Logistics
I-031 | P01 | 2026-01-04 | Pump discharge line leaking | Medium | K. Conde | Resolved | 2026-01-11 | 7 |  | Poor installation
I-032 | P01 | 2026-03-02 | Blast delayed – explosives truck late | High | A. Camara | Resolved | 2026-03-11 | 9 |  | Logistics
I-033 | P05 | 2026-06-14 | Pump discharge line leaking | Critical | F. Bah | Resolved | 2026-06-17 | 3 |  | Poor installation
I-034 | P08 | 2026-01-26 | Dust complaint from village | Critical | O. Traore | Resolved | 2026-02-13 | 18 |  | Water cart breakdown
I-035 | P03 | 2026-02-26 | Contractor invoice disputed | Critical | S. Keita | Resolved | 2026-03-16 | 18 |  | Unclear rates
I-036 | P05 | 2026-07-23 | ERP user access not granted | Medium | O. Traore | Resolved | 2026-07-30 | 7 |  | IT approval workflow
I-037 | P07 | 2026-01-10 | Pump discharge line leaking | Critical | K. Conde | Resolved | 2026-01-24 | 14 |  | Poor installation
I-038 | P01 | 2026-04-13 | Contractor invoice disputed | Low | S. Keita | Resolved | 2026-04-17 | 4 |  | Unclear rates
I-039 | P06 | 2026-07-04 | Survey pickup missing for bench 3 | Low | S. Keita | Resolved | 2026-07-11 | 7 |  | Surveyor rostered off
I-040 | P03 | 2026-03-01 | Excavator breakdown – no spare boom cylinder | Low | M. Diallo | Resolved | 2026-03-19 | 18 |  | Spares stock-out
Formulas:
Days open (if open) = IF(OR([Date raised]="",[Date resolved]<>""),"",TODAY()-[Date raised])

## Stakeholder_Survey
Stakeholder Satisfaction Survey
Score each criterion 1 (very poor) to 5 (excellent). Overall = average of the four criteria.
Survey date | Project ID | Stakeholder name | Stakeholder group | Communication | Delivery vs plan | Quality of outputs | Responsiveness | Overall score | Comments
2026-01-23 | P06 | Stakeholder 1 | Subcontractor | 4 | 4 | 4 | 4 | 4
2026-02-07 | P02 | Stakeholder 2 | Internal – Management | 2 | 4 | 4 | 3 | 3.25
2026-03-09 | P01 | Stakeholder 3 | Internal – Management | 3 | 4 | 3 | 3 | 3.25
2026-04-24 | P03 | Stakeholder 4 | Client – Owner's team | 3 | 3 | 4 | 4 | 3.5
2026-05-23 | P04 | Stakeholder 5 | Client – Mine Manager | 3 | 4 | 4 | 4 | 3.75
2026-06-12 | P04 | Stakeholder 6 | Client – Mine Manager | 5 | 3 | 3 | 3 | 3.5
2026-07-15 | P02 | Stakeholder 7 | Internal – Management | 3 | 3 | 4 | 4 | 3.5
2026-08-18 | P05 | Stakeholder 8 | Subcontractor | 4 | 5 | 3 | 4 | 4
2026-09-10 | P01 | Stakeholder 9 | Client – Mine Manager | 4 | 4 | 4 | 5 | 4.25
2026-10-19 | P03 | Stakeholder 10 | Internal – Management | 4 | 4 | 4 | 5 | 4.25
2026-01-19 | P01 | Stakeholder 11 | Client – Mine Manager | 3 | 3 | 3 | 2 | 2.75
2026-02-21 | P02 | Stakeholder 12 | Client – Mine Manager | 4 | 2 | 3 | 3 | 3
2026-03-05 | P02 | Stakeholder 13 | Subcontractor | 3 | 3 | 4 | 5 | 3.75
2026-04-20 | P05 | Stakeholder 14 | Client – Owner's team | 3 | 3 | 4 | 5 | 3.75
2026-05-24 | P05 | Stakeholder 15 | Client – Owner's team | 3 | 4 | 4 | 3 | 3.5
2026-06-13 | P08 | Stakeholder 16 | Client – Owner's team | 3 | 3 | 4 | 4 | 3.5
2026-07-11 | P03 | Stakeholder 17 | Internal – Management | 5 | 5 | 3 | 3 | 4
2026-08-10 | P05 | Stakeholder 18 | Client – Mine Manager | 4 | 4 | 5 | 3 | 4
2026-09-19 | P02 | Stakeholder 19 | Community | 5 | 4 | 3 | 5 | 4.25
2026-10-13 | P07 | Stakeholder 20 | Community | 4 | 4 | 4 | 3 | 3.75
2026-01-10 | P01 | Stakeholder 21 | Community | 4 | 3 | 2 | 2 | 2.75
2026-02-23 | P06 | Stakeholder 22 | Client – Mine Manager | 4 | 3 | 3 | 4 | 3.5
2026-03-18 | P06 | Stakeholder 23 | Client – Mine Manager | 4 | 4 | 4 | 4 | 4
2026-04-05 | P06 | Stakeholder 24 | Community | 4 | 4 | 4 | 4 | 4
2026-05-23 | P03 | Stakeholder 25 | Client – Owner's team | 3 | 5 | 4 | 4 | 4
2026-06-12 | P03 | Stakeholder 26 | Internal – Management | 5 | 4 | 5 | 3 | 4.25
2026-07-17 | P05 | Stakeholder 27 | Client – Mine Manager | 5 | 4 | 5 | 3 | 4.25
2026-08-23 | P08 | Stakeholder 28 | Subcontractor | 5 | 4 | 4 | 5 | 4.5
2026-09-06 | P01 | Stakeholder 29 | Subcontractor | 4 | 4 | 5 | 5 | 4.5
2026-10-08 | P01 | Stakeholder 30 | Subcontractor | 3 | 4 | 4 | 4 | 3.75
2026-01-24 | P07 | Stakeholder 31 | Subcontractor | 4 | 4 | 3 | 4 | 3.75
2026-02-20 | P01 | Stakeholder 32 | Internal – Management | 4 | 3 | 3 | 4 | 3.5
2026-03-19 | P03 | Stakeholder 33 | Client – Owner's team | 4 | 4 | 3 | 3 | 3.5
2026-04-13 | P01 | Stakeholder 34 | Community | 3 | 3 | 3 | 2 | 2.75
2026-05-13 | P05 | Stakeholder 35 | Client – Owner's team | 4 | 4 | 4 | 5 | 4.25
2026-06-11 | P03 | Stakeholder 36 | Community | 4 | 4 | 3 | 3 | 3.5

## Resources
Resource Utilisation & Team Productivity – monthly per team
Available = paid/rostered hours. Allocated = hours booked to project work. Output unit is team-specific (e.g. m drilled, t moved).
Month | Team / resource | Discipline | Available hours | Allocated project hours | Utilisation | Output unit | Planned output | Actual output | Productivity (actual/plan) | Remarks
2026-01-01 | Drill & Blast crew | Drill & Blast | 2080 | 1726 | 82.98% | m drilled | 9000 | 8743 | 97.14%
2026-01-01 | Load & Haul crew | Mining | 1760 | 1589 | 90.28% | kt moved | 900 | 857 | 95.22%
2026-01-01 | Maintenance team | Maintenance | 1840 | 1561 | 84.84% | work orders | 160 | 148 | 92.5%
2026-01-01 | Projects & Engineering | Engineering | 1840 | 1498 | 81.41% | deliverables | 24 | 24 | 100%
2026-02-01 | Drill & Blast crew | Drill & Blast | 1840 | 1412 | 76.74% | m drilled | 9000 | 7791 | 86.57%
2026-02-01 | Load & Haul crew | Mining | 1760 | 1510 | 85.8% | kt moved | 900 | 805 | 89.44%
2026-02-01 | Maintenance team | Maintenance | 1840 | 1607 | 87.34% | work orders | 160 | 139 | 86.88%
2026-02-01 | Projects & Engineering | Engineering | 1840 | 1604 | 87.17% | deliverables | 24 | 24 | 100%
2026-03-01 | Drill & Blast crew | Drill & Blast | 1760 | 1549 | 88.01% | m drilled | 9000 | 7864 | 87.38%
2026-03-01 | Load & Haul crew | Mining | 1920 | 1494 | 77.81% | kt moved | 900 | 954 | 106%
2026-03-01 | Maintenance team | Maintenance | 1760 | 1597 | 90.74% | work orders | 160 | 163 | 101.9%
2026-03-01 | Projects & Engineering | Engineering | 2080 | 1582 | 76.06% | deliverables | 24 | 22 | 91.67%
2026-04-01 | Drill & Blast crew | Drill & Blast | 1760 | 1314 | 74.66% | m drilled | 9000 | 9534 | 105.9%
2026-04-01 | Load & Haul crew | Mining | 1760 | 1578 | 89.66% | kt moved | 900 | 893 | 99.22%
2026-04-01 | Maintenance team | Maintenance | 1920 | 1595 | 83.07% | work orders | 160 | 142 | 88.75%
2026-04-01 | Projects & Engineering | Engineering | 1840 | 1465 | 79.62% | deliverables | 24 | 22 | 91.67%
2026-05-01 | Drill & Blast crew | Drill & Blast | 1920 | 1428 | 74.38% | m drilled | 9000 | 8225 | 91.39%
2026-05-01 | Load & Haul crew | Mining | 1920 | 1438 | 74.9% | kt moved | 900 | 918 | 102%
2026-05-01 | Maintenance team | Maintenance | 1920 | 1701 | 88.59% | work orders | 160 | 158 | 98.75%
2026-05-01 | Projects & Engineering | Engineering | 2080 | 1876 | 90.19% | deliverables | 24 | 24 | 100%
2026-06-01 | Drill & Blast crew | Drill & Blast | 1760 | 1566 | 88.98% | m drilled | 9000 | 7799 | 86.66%
2026-06-01 | Load & Haul crew | Mining | 1760 | 1418 | 80.57% | kt moved | 900 | 907 | 100.8%
2026-06-01 | Maintenance team | Maintenance | 1840 | 1611 | 87.55% | work orders | 160 | 165 | 103.1%
2026-06-01 | Projects & Engineering | Engineering | 1920 | 1483 | 77.24% | deliverables | 24 | 21 | 87.5%
2026-07-01 | Drill & Blast crew | Drill & Blast | 1840 | 1462 | 79.46% | m drilled | 9000 | 9158 | 101.8%
2026-07-01 | Load & Haul crew | Mining | 1760 | 1304 | 74.09% | kt moved | 900 | 867 | 96.33%
2026-07-01 | Maintenance team | Maintenance | 2080 | 1814 | 87.21% | work orders | 160 | 165 | 103.1%
2026-07-01 | Projects & Engineering | Engineering | 2080 | 1773 | 85.24% | deliverables | 24 | 25 | 104.2%
2026-08-01 | Drill & Blast crew | Drill & Blast | 1920 | 1632 | 85% | m drilled | 9000 | 8040 | 89.33%
2026-08-01 | Load & Haul crew | Mining | 1840 | 1690 | 91.85% | kt moved | 900 | 818 | 90.89%
2026-08-01 | Maintenance team | Maintenance | 1840 | 1400 | 76.09% | work orders | 160 | 159 | 99.38%
2026-08-01 | Projects & Engineering | Engineering | 1760 | 1466 | 83.3% | deliverables | 24 | 26 | 108.3%
2026-09-01 | Drill & Blast crew | Drill & Blast | 1760 | 1512 | 85.91% | m drilled | 9000 | 8412 | 93.47%
2026-09-01 | Load & Haul crew | Mining | 2080 | 1906 | 91.63% | kt moved | 900 | 943 | 104.8%
2026-09-01 | Maintenance team | Maintenance | 1760 | 1444 | 82.05% | work orders | 160 | 159 | 99.38%
2026-09-01 | Projects & Engineering | Engineering | 1920 | 1496 | 77.92% | deliverables | 24 | 22 | 91.67%
2026-10-01 | Drill & Blast crew | Drill & Blast | 1840 | 1494 | 81.2% | m drilled | 9000 | 9411 | 104.6%
2026-10-01 | Load & Haul crew | Mining | 1840 | 1692 | 91.96% | kt moved | 900 | 798 | 88.67%
2026-10-01 | Maintenance team | Maintenance | 1760 | 1419 | 80.62% | work orders | 160 | 149 | 93.12%
2026-10-01 | Projects & Engineering | Engineering | 1840 | 1665 | 90.49% | deliverables | 24 | 23 | 95.83%

## Milestones
Milestone Tracker
Keep the BASELINE due date fixed. Enter the actual completion date when done. On time? compares the two.
Milestone ID | Project ID | Milestone | Owner | Baseline due date | Actual / forecast completion | Status | On time? | Days late (+) / early (−) | Remarks
M-001 | P03 | Go-live | B. Toure | 2026-01-20 | 2026-01-23 | Completed | No | 3
M-002 | P04 | Procurement complete | K. Conde | 2026-02-25 | 2026-02-26 | Completed | No | 1
M-003 | P04 | Commissioning | I. Sylla | 2026-03-17 | 2026-03-17 | Completed | Yes | 0
M-004 | P03 | Procurement complete | F. Bah | 2026-04-27 | 2026-04-27 | Completed | Yes | 0
M-005 | P06 | Procurement complete | F. Bah | 2026-05-26 | 2026-05-29 | Completed | No | 3
M-006 | P05 | Mobilisation complete | S. Keita | 2026-06-13 | 2026-06-13 | Completed | Yes | 0
M-007 | P04 | Trial blast completed | S. Keita | 2026-07-24 | 2026-07-22 | Completed | Yes | -2
M-008 | P05 | Trial blast completed | I. Sylla | 2026-08-07 | 2026-08-08 | Completed | No | 1
M-009 | P02 | Commissioning | F. Bah | 2026-09-09 | 2026-09-07 | Completed | Yes | -2
M-010 | P07 | Trial blast completed | F. Bah | 2026-10-15 | 2026-10-10 | Completed | Yes | -5
M-011 | P08 | Design approved | S. Keita | 2026-01-19 | 2026-01-20 | Completed | No | 1
M-012 | P07 | Design approved | F. Bah | 2026-02-11 | 2026-02-11 | Completed | Yes | 0
M-013 | P07 | 50% construction | F. Bah | 2026-03-16 | 2026-03-16 | Completed | Yes | 0
M-014 | P02 | Go-live | O. Traore | 2026-04-24 | 2026-04-24 | Completed | Yes | 0
M-015 | P02 | Trial blast completed | F. Bah | 2026-05-13 | 2026-05-14 | Completed | No | 1
M-016 | P03 | Commissioning | O. Traore | 2026-06-28 | 2026-07-04 | Completed | No | 6
M-017 | P01 | Trial blast completed | S. Keita | 2026-07-18 | 2026-07-28 | Completed | No | 10
M-018 | P01 | Trial blast completed | B. Toure | 2026-08-23 | 2026-08-26 | Completed | No | 3
M-019 | P05 | 50% construction | S. Keita | 2026-09-06 | 2026-09-01 | Completed | Yes | -5
M-020 | P04 | Handover | M. Diallo | 2026-10-25 |  | In progress | Overdue
M-021 | P04 | Go-live | A. Camara | 2026-01-21 | 2026-01-31 | Completed | No | 10
M-022 | P06 | Trial blast completed | B. Toure | 2026-02-23 | 2026-02-26 | Completed | No | 3
M-023 | P07 | Mobilisation complete | K. Conde | 2026-03-09 | 2026-03-09 | Completed | Yes | 0
M-024 | P05 | Commissioning | O. Traore | 2026-04-23 | 2026-04-18 | Completed | Yes | -5
M-025 | P01 | Mobilisation complete | O. Traore | 2026-05-15 | 2026-05-10 | Completed | Yes | -5
M-026 | P05 | Mobilisation complete | F. Bah | 2026-06-16 | 2026-06-19 | Completed | No | 3
M-027 | P04 | Trial blast completed | B. Toure | 2026-07-12 | 2026-07-18 | Completed | No | 6
M-028 | P03 | Mobilisation complete | F. Bah | 2026-08-09 | 2026-08-09 | Completed | Yes | 0
M-029 | P04 | Procurement complete | K. Conde | 2026-09-18 | 2026-09-17 | Completed | Yes | -1
M-030 | P07 | Go-live | I. Sylla | 2026-10-24 |  | In progress | Overdue
M-031 | P03 | Go-live | K. Conde | 2026-01-27 | 2026-01-26 | Completed | Yes | -1
M-032 | P05 | Trial blast completed | I. Sylla | 2026-02-28 | 2026-02-28 | Completed | Yes | 0
M-033 | P08 | Design approved | I. Sylla | 2026-03-16 | 2026-03-16 | Completed | Yes | 0
M-034 | P05 | Handover | B. Toure | 2026-04-14 | 2026-04-14 | Completed | Yes | 0
M-035 | P02 | Handover | S. Keita | 2026-05-18 | 2026-05-24 | Completed | No | 6
M-036 | P01 | Mobilisation complete | K. Conde | 2026-06-12 | 2026-06-18 | Completed | No | 6
M-037 | P06 | Design approved | A. Camara | 2026-07-28 | 2026-07-28 | Completed | Yes | 0
M-038 | P05 | Commissioning | M. Diallo | 2026-08-09 | 2026-08-07 | Completed | Yes | -2
M-039 | P04 | Procurement complete | B. Toure | 2026-09-21 | 2026-09-21 | Completed | Yes | 0
M-040 | P04 | Trial blast completed | S. Keita | 2026-10-14 |  | In progress | Overdue
M-041 | P02 | Commissioning | F. Bah | 2026-01-22 | 2026-01-22 | Completed | Yes | 0
M-042 | P02 | Go-live | M. Diallo | 2026-02-18 | 2026-02-18 | Completed | Yes | 0
M-043 | P05 | Trial blast completed | F. Bah | 2026-03-20 | 2026-03-18 | Completed | Yes | -2
M-044 | P08 | Design approved | B. Toure | 2026-04-07 | 2026-04-17 | Completed | No | 10
M-045 | P08 | 50% construction | B. Toure | 2026-05-17 | 2026-05-17 | Completed | Yes | 0
M-046 | P01 | Procurement complete | K. Conde | 2026-06-08 | 2026-06-07 | Completed | Yes | -1
Formulas:
On time? = IF([Baseline due date]="","",IF([Status]<>"Completed",IF([Baseline due date]<TODAY(),"Overdue",""),IF([Actual / forecast completion]<=[Baseline due date],"Yes","No")))

## Quality_Log
Quality – Deliverable Inspection Log
One row per deliverable inspection. 'Accepted first time' = passed with no rework.
Inspection ID | Project ID | Deliverable | Inspection date | Inspector | Defects found | Accepted first time? | Rework hours | Rework cost | Defect description / root cause
Q-001 | P08 | Road section compaction test | 2026-01-16 | K. Conde | 0 | Yes | 0 | 0
Q-002 | P02 | Concrete foundation pour | 2026-02-22 | K. Conde | 0 | Yes | 0 | 0
Q-003 | P01 | Bench survey as-built | 2026-03-21 | A. Camara | 0 | Yes | 0 | 0
Q-004 | P06 | Blast design pack | 2026-04-18 | B. Toure | 0 | Yes | 0 | 0
Q-005 | P03 | Bench survey as-built | 2026-05-08 | O. Traore | 0 | Yes | 0 | 0
Q-006 | P06 | Blast design pack | 2026-06-23 | K. Conde | 0 | Yes | 0 | 0
Q-007 | P04 | Road section compaction test | 2026-07-15 | K. Conde | 0 | Yes | 0 | 0
Q-008 | P01 | Road section compaction test | 2026-08-11 | K. Conde | 0 | Yes | 0 | 0
Q-009 | P07 | Pump station install | 2026-09-18 | I. Sylla | 0 | Yes | 0 | 0
Q-010 | P06 | Rebuilt truck acceptance | 2026-10-22 | B. Toure | 0 | Yes | 0 | 0
Q-011 | P06 | Rebuilt truck acceptance | 2026-01-12 | I. Sylla | 0 | Yes | 0 | 0
Q-012 | P02 | Bench survey as-built | 2026-02-14 | O. Traore | 0 | Yes | 0 | 0
Q-013 | P01 | ERP module UAT | 2026-03-11 | M. Diallo | 0 | Yes | 0 | 0
Q-014 | P04 | Accommodation block handover | 2026-04-21 | A. Camara | 0 | Yes | 0 | 0
Q-015 | P07 | Concrete foundation pour | 2026-05-22 | M. Diallo | 0 | Yes | 0 | 0
Q-016 | P08 | Concrete foundation pour | 2026-06-05 | S. Keita | 0 | Yes | 0 | 0
Q-017 | P07 | Blast design pack | 2026-07-22 | A. Camara | 0 | Yes | 0 | 0
Q-018 | P03 | Road section compaction test | 2026-08-19 | I. Sylla | 0 | Yes | 0 | 0
Q-019 | P03 | ERP module UAT | 2026-09-03 | K. Conde | 0 | Yes | 0 | 0
Q-020 | P01 | Accommodation block handover | 2026-10-20 | A. Camara | 0 | Yes | 0 | 0
Q-021 | P07 | ERP module UAT | 2026-01-16 | M. Diallo | 0 | Yes | 0 | 0
Q-022 | P07 | Concrete foundation pour | 2026-02-17 | O. Traore | 0 | Yes | 0 | 0
Q-023 | P02 | Accommodation block handover | 2026-03-08 | S. Keita | 0 | Yes | 0 | 0
Q-024 | P07 | Bench survey as-built | 2026-04-02 | M. Diallo | 0 | Yes | 0 | 0
Q-025 | P02 | Concrete foundation pour | 2026-05-17 | A. Camara | 1 | No | 17 | 765 | Workmanship
Q-026 | P04 | Accommodation block handover | 2026-06-25 | S. Keita | 0 | Yes | 0 | 0
Q-027 | P02 | Road section compaction test | 2026-07-22 | B. Toure | 3 | No | 13 | 585 | Wrong material spec
Q-028 | P05 | Bench survey as-built | 2026-08-24 | A. Camara | 0 | Yes | 0 | 0
Q-029 | P01 | Blast design pack | 2026-09-14 | I. Sylla | 0 | Yes | 0 | 0
Q-030 | P03 | Accommodation block handover | 2026-10-21 | A. Camara | 0 | Yes | 0 | 0
Q-031 | P08 | Accommodation block handover | 2026-01-23 | S. Keita | 0 | Yes | 0 | 0
Q-032 | P02 | Pump station install | 2026-02-22 | S. Keita | 0 | Yes | 0 | 0
Q-033 | P07 | Accommodation block handover | 2026-03-14 | B. Toure | 0 | Yes | 0 | 0
Q-034 | P05 | Road section compaction test | 2026-04-03 | K. Conde | 5 | No | 25 | 1125 | Out of tolerance
Q-035 | P05 | ERP module UAT | 2026-05-09 | O. Traore | 0 | Yes | 0 | 0
Q-036 | P07 | Rebuilt truck acceptance | 2026-06-27 | B. Toure | 0 | Yes | 0 | 0
Q-037 | P01 | Pump station install | 2026-07-10 | I. Sylla | 0 | Yes | 0 | 0
Q-038 | P01 | Road section compaction test | 2026-08-06 | S. Keita | 0 | Yes | 0 | 0
Q-039 | P08 | Pump station install | 2026-09-19 | M. Diallo | 0 | Yes | 0 | 0
Q-040 | P08 | ERP module UAT | 2026-10-08 | F. Bah | 0 | Yes | 0 | 0
Q-041 | P01 | ERP module UAT | 2026-01-16 | F. Bah | 0 | Yes | 0 | 0
Q-042 | P07 | Accommodation block handover | 2026-02-19 | M. Diallo | 5 | No | 4 | 180 | Workmanship
Q-043 | P04 | ERP module UAT | 2026-03-20 | I. Sylla | 0 | Yes | 0 | 0
Q-044 | P08 | Rebuilt truck acceptance | 2026-04-08 | F. Bah | 5 | No | 24 | 1080 | Missing documentation
Q-045 | P05 | Pump station install | 2026-05-20 | K. Conde | 0 | Yes | 0 | 0
Q-046 | P03 | Rebuilt truck acceptance | 2026-06-03 | B. Toure | 0 | Yes | 0 | 0
Q-047 | P02 | Pump station install | 2026-07-22 | B. Toure | 0 | Yes | 0 | 0
Q-048 | P03 | Pump station install | 2026-08-21 | A. Camara | 0 | Yes | 0 | 0

## Benefits_Log
Benefits Realisation Log
Re-measure each benefit periodically (monthly/quarterly). Planned and realised values are CUMULATIVE to the measurement date, in the same unit.
Benefit ID | Project ID | Benefit description | Measure / unit | Measurement date | Planned value (cumulative) | Realised value (cumulative) | Realisation % | Benefit owner | Remarks
B01 | P02 | Haul cycle time reduction – fuel saving | USD saved | 2026-04-28 | 25000 | 22915 | 91.66% | A. Camara
B01 | P02 | Haul cycle time reduction – fuel saving | USD saved | 2026-05-28 | 50000 | 44281 | 88.56% | F. Bah
B01 | P02 | Haul cycle time reduction – fuel saving | USD saved | 2026-06-28 | 75000 | 74724 | 99.63% | B. Toure
B01 | P02 | Haul cycle time reduction – fuel saving | USD saved | 2026-07-28 | 100000 | 94646 | 94.65% | F. Bah
B01 | P02 | Haul cycle time reduction – fuel saving | USD saved | 2026-08-28 | 125000 | 113288 | 90.63% | I. Sylla
B01 | P02 | Haul cycle time reduction – fuel saving | USD saved | 2026-09-28 | 150000 | 138991 | 92.66% | B. Toure
B01 | P02 | Haul cycle time reduction – fuel saving | USD saved | 2026-10-28 | 175000 | 169532 | 96.88% | S. Keita
B02 | P04 | Reduced secondary breaking cost | USD saved | 2026-06-28 | 18000 | 13380 | 74.33% | A. Camara
B02 | P04 | Reduced secondary breaking cost | USD saved | 2026-07-28 | 36000 | 27071 | 75.2% | S. Keita
B02 | P04 | Reduced secondary breaking cost | USD saved | 2026-08-28 | 54000 | 40821 | 75.59% | A. Camara
B02 | P04 | Reduced secondary breaking cost | USD saved | 2026-09-28 | 72000 | 52040 | 72.28% | K. Conde
B02 | P04 | Reduced secondary breaking cost | USD saved | 2026-10-28 | 90000 | 72530 | 80.59% | B. Toure
B03 | P03 | Truck availability uplift – extra tonnes | kt moved | 2026-08-28 | 60 | 53 | 88.33% | M. Diallo
B03 | P03 | Truck availability uplift – extra tonnes | kt moved | 2026-09-28 | 120 | 111 | 92.5% | O. Traore
B03 | P03 | Truck availability uplift – extra tonnes | kt moved | 2026-10-28 | 180 | 168 | 93.33% | M. Diallo
B04 | P08 | Reduced bussing cost (on-site beds) | USD saved | 2026-09-28 | 12000 | 11670 | 97.25% | F. Bah
B04 | P08 | Reduced bussing cost (on-site beds) | USD saved | 2026-10-28 | 24000 | 24560 | 102.3% | O. Traore

## CI_Log
Continuous Improvement Initiatives
Improvements to HOW projects are delivered. Count implemented per month = KPI; 'Benefit verified' checks they actually worked.
CI ID | Date proposed | Initiative | KPI targeted | Owner | Status | Implementation date | Expected benefit | Benefit verified? | Verified result | Remarks
CI-001 | 2026-01-03 | Weekly look-ahead planning meeting | Milestone Completion Rate | K. Conde | Implemented | 2026-01-27 | Milestones hit on time | Yes | See monthly KPI trend
CI-002 | 2026-01-04 | Standard CR form with 48h review SLA | Change Request Approval Time | S. Keita | Implemented | 2026-02-06 | CR decided within 5 days | Yes | See monthly KPI trend
CI-003 | 2026-02-01 | Daily issue triage at pre-start | Issue Resolution Time | A. Camara | Implemented | 2026-02-19 | Issues closed in < 7 days | Yes | See monthly KPI trend
CI-004 | 2026-03-15 | EVM reporting template for all projects | Project Schedule Variance (SV%) | A. Camara | Implemented | 2026-04-11 | Early schedule-slip detection | Yes | See monthly KPI trend
CI-005 | 2026-03-05 | Pre-pour QA checklist | Project Quality Index | B. Toure | Implemented | 2026-04-09 | Fewer concrete rejections | No
CI-006 | 2026-04-01 | Monthly stakeholder pulse survey | Stakeholder Satisfaction | K. Conde | Implemented | 2026-04-14 | Earlier complaint detection | Yes | See monthly KPI trend
CI-007 | 2026-05-13 | Critical spares min/max review | Resource Utilization Rate | I. Sylla | Implemented | 2026-05-23 | Less idle crew time | Yes | See monthly KPI trend
CI-008 | 2026-06-10 | Risk review in monthly meeting | Risk Mitigation Effectiveness | M. Diallo | Implemented | 2026-07-08 | Fewer risks materialising | Yes | See monthly KPI trend
CI-009 | 2026-06-08 | Post-project lessons-learned workshop | Project Success Rate | I. Sylla | Implemented | 2026-06-28 | Repeat mistakes avoided | Yes | See monthly KPI trend
CI-010 | 2026-07-07 | Scope freeze gate before execution | Scope Change Frequency | B. Toure | Implemented | 2026-07-20 | Fewer scope changes | Yes | See monthly KPI trend
CI-011 | 2026-08-07 | Blast design peer review | Project Quality Index | F. Bah | Implemented | 2026-08-22 | Fewer redrills | Yes | See monthly KPI trend
CI-012 | 2026-08-13 | Benefits owner sign-off at closure | Benefits Realization | A. Camara | Approved |  | Benefits tracked after handover
CI-013 | 2026-09-08 | Shift handover app | Team Productivity Index | F. Bah | Proposed |  | Productivity +3%
CI-014 | 2026-10-13 | Supplier performance scorecard | Budget Utilization | S. Keita | Approved |  | Lower overspend

## Settings
Settings & Lists
Yellow cells are editable. Lists feed the drop-downs in every log.
|  | Project Status | Yes/No | Direction | Priority | Change Type | CR Decision | Risk Status | Risk Category | Issue Status | Milestone Status | Action Status | CI Status | Owners
Organisation / portfolio name | Mining Services – Project Portfolio | Not started | Yes | Higher | Critical | Scope | Pending | Open | Safety | Open | Not started | Open | Proposed | A. Camara
Reporting year start (1st of month) | 2026-01-01 | Active | No | Lower | High | Schedule | Approved | Mitigated | Technical | In progress | In progress | In progress | Approved | M. Diallo
Current reporting month (1st of month) | 2026-10-01 | On hold |  |  | Medium | Cost | Rejected | Closed | Commercial | Resolved | Completed | Implemented | In progress | S. Keita
Budget tolerance for 'within budget' | 5% | Completed |  |  | Low | Quality |  | Occurred | Schedule |  |  | Cancelled | Implemented | F. Bah
Prepared by | Project Controls | Cancelled |  |  |  | Resource |  |  | Environmental |  |  |  | Rejected | I. Sylla
[9 empty] | Community |  |  |  |  | K. Conde
[9 empty] | Supply chain |  |  |  |  | O. Traore
B. Toure
Tip: add owners/categories below the existing items in a list column (Owners accepts up to row 30).
Note on B6: Months AFTER this date are left blank in KPI_Tracking. Defaults to the current month; overwrite with a fixed date to freeze a reporting period.
Note on B7: A completed project is 'within budget' if Final cost <= BAC x (1 + tolerance).